## Risk Register
FinTech Solutions — Cybersecurity GRC Risk Assessment
NIST SP 800-30 Risk Register ¦ Classification: CONFIDENTIAL ¦ Version 1.0 ¦ May 2025
Company: FinTech Solutions (500 Employees) |  |  |  | Scope: Cloud Portal · HR Systems · Physical Servers · Endpoints |  |  |  | Assessor: GRC Team ¦ Date: May 2025
Threat ID | Threat Category | Threat Event | Vulnerability | Business Impact Description | Likelihood (1–5) | Impact (1–5) | Inherent Risk Score | Mitigation Strategy | Residual Likelihood | Residual Impact | Residual Risk Score
TR-01 | Adversarial | Phishing leading to credential theft | No MFA enforced; insufficient security awareness training | Attackers gain access to customer financial accounts causing regulatory fines up to $500K and reputational damage. | 4 | 4 | 16 | Enforce MFA across all systems; quarterly phishing simulations; deploy email filtering (DMARC/SPF/DKIM). | 2 | 2 | 4
TR-02 | Adversarial | Ransomware encrypting critical databases | Unpatched legacy Windows servers; no EDR solution | All business operations halted; estimated $50K/hr in lost transactions plus $2M ransom exposure. | 4 | 5 | 20 | Automated patch management; deploy EDR (CrowdStrike); immutable daily cloud backups; incident response plan. | 2 | 3 | 6
TR-03 | Adversarial | SQL injection on customer portal | Lack of input validation; no Web Application Firewall | Exposure of 50,000+ customer financial records; PCI-DSS non-compliance fines of $100K–$500K. | 3 | 5 | 15 | Deploy WAF (AWS WAF); enforce parameterized queries; conduct quarterly DAST/SAST scans. | 2 | 2 | 4
TR-04 | Adversarial | DDoS attack on cloud-hosted portal | No traffic rate-limiting or DDoS mitigation service | Customer portal unavailable for hours; estimated $50K/hr revenue loss; SLA breach penalties. | 3 | 4 | 12 | AWS Shield Advanced; auto-scaling; CloudFront CDN with rate limiting; runbook for failover. | 2 | 2 | 4
TR-05 | Adversarial | Man-in-the-Middle (MitM) on internal network | Weak network segmentation; unencrypted internal traffic | Interception of sensitive financial data in transit; regulatory exposure under PIPEDA. | 2 | 4 | 8 | TLS 1.2/1.3 everywhere; network segmentation with VLANs; 802.1X port authentication. | 1 | 2 | 2
TR-06 | Adversarial | Brute-force attack on admin accounts | No account lockout policy; weak password requirements | Full system admin access gained; potential for complete data breach. | 3 | 5 | 15 | Enforce account lockout after 5 attempts; require 16-char passphrases; privileged access workstation. | 2 | 2 | 4
TR-07 | Adversarial | Supply-chain software compromise (malicious update) | Third-party vendor software not vetted; no SBOM tracking | Backdoor introduced into production systems affecting all 500 employees and customer data. | 2 | 5 | 10 | Software Bill of Materials (SBOM); vendor security assessments; signed software releases only. | 1 | 3 | 3
TR-08 | Adversarial | Cloud misconfiguration exposing S3 buckets | No cloud security posture management (CSPM) in place | Publicly accessible customer records; PIPEDA breach notification required; $250K+ regulatory risk. | 4 | 4 | 16 | AWS Config + Security Hub; CSPM tool (Wiz/Prisma); automated remediation pipelines. | 2 | 2 | 4
TR-09 | Adversarial | API key leakage via public GitHub repository | Developers push secrets to public repos; no secrets scanning | Attackers access cloud infrastructure; potential full environment takeover. | 4 | 4 | 16 | Mandatory secrets scanning (GitGuardian); GitHub Advanced Security; vault-based secret management. | 2 | 2 | 4
TR-10 | Adversarial | Zero-day exploit targeting web server | No virtual patching mechanism; delayed patch cycle | Unanticipated code execution on web tier; lateral movement to database layer possible. | 2 | 5 | 10 | IDS/IPS with virtual patching; threat intelligence feed subscription; 24hr patch SLA. | 1 | 3 | 3
TR-11 | Insider Threat | Disgruntled employee exfiltrating customer data | Excessive access privileges; no DLP monitoring | Mass exfiltration of financial records; breach notification costs $1M+; class-action risk. | 3 | 5 | 15 | Role-based access control (RBAC); DLP tool (Microsoft Purview); employee offboarding checklist. | 2 | 2 | 4
TR-12 | Insider Threat | Accidental data disclosure via email | No email DLP; lack of data classification training | PII sent to wrong recipient; PIPEDA breach notification required; reputational harm. | 4 | 3 | 12 | Email DLP with auto-block on PII patterns; data classification training annually. | 2 | 2 | 4
TR-13 | Insider Threat | Privileged user abusing admin access | Insufficient audit logging; no Privileged Access Management (PAM) | Unauthorized configuration changes; potential backdoor creation in production systems. | 2 | 4 | 8 | Deploy CyberArk PAM; session recording for all privileged sessions; quarterly access reviews. | 1 | 2 | 2
TR-14 | Insider Threat | Shadow IT — unauthorized cloud service use | No cloud app policy; employees use unapproved SaaS tools | Sensitive data stored in unsanctioned apps outside corporate DLP controls. | 4 | 3 | 12 | CASB (Netskope); acceptable-use policy; block unapproved cloud apps via proxy. | 2 | 2 | 4
TR-15 | Accidental | IT admin accidentally deletes production database | No automated backups; no change management process | Total loss of customer transaction history; estimated 72-hour recovery time costing $3.6M in downtime. | 3 | 5 | 15 | Automated daily backups (RPO < 1hr); CAB change approval process; immutable backup snapshots. | 1 | 3 | 3
TR-16 | Accidental | Misconfigured firewall rule opens internal ports | Manual firewall management; no configuration drift detection | Internal services exposed to internet; enables lateral movement by attackers. | 3 | 4 | 12 | Infrastructure-as-Code (Terraform) for firewall rules; automated drift detection (AWS Config). | 2 | 2 | 4
TR-17 | Accidental | Employee loses unencrypted laptop with PII | Full-disk encryption not enforced on all endpoints | Breach notification to 10,000+ customers; PIPEDA fines; $200K remediation cost. | 3 | 4 | 12 | Mandatory BitLocker/FileVault on all endpoints; MDM enforcement via Intune; remote wipe capability. | 1 | 2 | 2
TR-18 | Environmental | Extended power outage at main office | No backup generator; UPS capacity <15 minutes | All on-premise servers offline; 4-hour average outage = $200K revenue impact. | 2 | 3 | 6 | Install diesel backup generator; extend UPS to 2hr; migrate critical workloads to cloud. | 1 | 2 | 2
TR-19 | Environmental | Flood / water damage to server room | Server room in basement; no raised floor or leak detection | Physical destruction of primary servers; estimated $500K hardware replacement plus data loss risk. | 1 | 5 | 5 | Relocate server room to upper floor; install water leak sensors; disaster recovery site. | 1 | 2 | 2
TR-20 | Environmental | Unauthorized physical access to server room | Tailgating risk; badge-only access without logging | Physical tampering with servers; potential hardware implants or data theft. | 2 | 4 | 8 | Mantraps / dual-factor physical access; security cameras; quarterly access log reviews. | 1 | 2 | 2
TR-21 | Compliance | Failure to notify regulators within 72hrs of breach | No documented incident response plan; unclear ownership | PIPEDA maximum penalties; regulatory sanctions; loss of operating license risk. | 3 | 4 | 12 | Documented IRP with legal review; CIRT on retainer; tabletop exercises bi-annually. | 1 | 2 | 2
TR-22 | Compliance | Unencrypted PII stored in legacy flat files | Data inventory not maintained; legacy systems with no encryption-at-rest | Non-compliance with PIPEDA; mandatory breach disclosure even for internal access events. | 3 | 4 | 12 | Full data inventory (data discovery scan); encrypt all datastores at rest (AES-256). | 2 | 2 | 4
TR-23 | Operational | Vendor/third-party experiencing a data breach | No third-party risk management (TPRM) program | Customer data held by vendor exposed; reputational damage; regulatory liability shared. | 3 | 4 | 12 | Annual vendor security assessments; contractual data protection clauses; vendor scorecard. | 2 | 2 | 4
TR-24 | Operational | Expired TLS certificate causing portal outage | Manual certificate management; no automated renewal | Customer portal inaccessible; $50K/hr revenue loss; trust erosion. | 3 | 3 | 9 | Automated cert renewal (AWS ACM / Let's Encrypt); PagerDuty alert 30 days before expiry. | 1 | 2 | 2
PORTFOLIO SUMMARY — Average Risk Scores
Estimated Risk Reduction: 73% |  |  |  |  | 2.9167 | 4.1667 | 12 |  | 1.5417 | 2.1667 | 3.2917

## Risk Heat Map
Risk Heat Map — NIST SP 800-30 ¦ 5×5 Likelihood × Impact Matrix
LEGEND: |  | Low Risk (1–6) |  | Medium Risk (8–12) |  | High / Critical Risk (15–25)
LIKELIHOOD ↓ IMPACT → | Impact 1 | Impact 2 | Impact 3 | Impact 4 | Impact 5
Likelihood 5 | Score: 5 | Score: 10 | Score: 15 | Score: 20 | Score: 25
Likelihood 4 | Score: 4 | Score: 8 | Score: 12 TR-12 TR-14 | Score: 16 TR-01 TR-08 TR-09 | Score: 20 TR-02
Likelihood 3 | Score: 3 | Score: 6 | Score: 9 TR-24 | Score: 12 TR-04 TR-16 TR-17 TR-21 TR-22 TR-23 | Score: 15 TR-03 TR-06 TR-11 TR-15
Likelihood 2 | Score: 2 | Score: 4 | Score: 6 TR-18 | Score: 8 TR-05 TR-13 TR-20 | Score: 10 TR-07 TR-10
Likelihood 1 | Score: 1 | Score: 2 | Score: 3 | Score: 4 | Score: 5 TR-19
RISK REDUCTION SUMMARY — Inherent vs. Residual
Threat ID | Threat Event | Inherent Score | Residual Score | Reduction | Risk Level → After
TR-01 | Phishing leading to credential theft | 16 | 4 | 75% | LOW
TR-02 | Ransomware encrypting critical databases | 20 | 6 | 70% | LOW
TR-03 | SQL injection on customer portal | 15 | 4 | 73.33% | LOW
TR-04 | DDoS attack on cloud-hosted portal | 12 | 4 | 66.67% | LOW
TR-05 | Man-in-the-Middle (MitM) on internal network | 8 | 2 | 75% | LOW
TR-06 | Brute-force attack on admin accounts | 15 | 4 | 73.33% | LOW
TR-07 | Supply-chain software compromise (malicious update) | 10 | 3 | 70% | LOW
TR-08 | Cloud misconfiguration exposing S3 buckets | 16 | 4 | 75% | LOW
TR-09 | API key leakage via public GitHub repository | 16 | 4 | 75% | LOW
TR-10 | Zero-day exploit targeting web server | 10 | 3 | 70% | LOW
TR-11 | Disgruntled employee exfiltrating customer data | 15 | 4 | 73.33% | LOW
TR-12 | Accidental data disclosure via email | 12 | 4 | 66.67% | LOW
TR-13 | Privileged user abusing admin access | 8 | 2 | 75% | LOW
TR-14 | Shadow IT — unauthorized cloud service use | 12 | 4 | 66.67% | LOW
TR-15 | IT admin accidentally deletes production database | 15 | 3 | 80% | LOW
TR-16 | Misconfigured firewall rule opens internal ports | 12 | 4 | 66.67% | LOW
TR-17 | Employee loses unencrypted laptop with PII | 12 | 2 | 83.33% | LOW
TR-18 | Extended power outage at main office | 6 | 2 | 66.67% | LOW
TR-19 | Flood / water damage to server room | 5 | 2 | 60% | LOW
TR-20 | Unauthorized physical access to server room | 8 | 2 | 75% | LOW
TR-21 | Failure to notify regulators within 72hrs of breach | 12 | 2 | 83.33% | LOW
TR-22 | Unencrypted PII stored in legacy flat files | 12 | 4 | 66.67% | LOW
TR-23 | Vendor/third-party experiencing a data breach | 12 | 4 | 66.67% | LOW
TR-24 | Expired TLS certificate causing portal outage | 9 | 2 | 77.78% | LOW

## Executive Dashboard
FinTech Solutions — Executive Risk Dashboard
NIST SP 800-30 Cybersecurity GRC Assessment ¦ May 2025 ¦ Prepared by: GRC Team
Total Threats Identified | Critical / High Risk Threats | Medium Risk Threats | Low Risk Threats | Residual High Risk Threats | Est. Risk Reduction
24 | 8 | 14 | 2 | 0 | 72.57%
Risk Distribution by Category
Category | Total Threats | Avg Inherent Score | Avg Residual Score | Avg Reduction | Max Inherent Score | Threats ≥ High | Mitigation Priority
Adversarial | 10 | 13.8 | 3.8 | 72.46% | 20 | 6 | IMMEDIATE
Insider Threat | 4 | 11.8 | 3.5 | 70.21% | 15 | 1 | HIGH
Accidental | 3 | 13 | 3 | 76.92% | 15 | 1 | HIGH
Environmental | 3 | 6.3 | 2 | 68.42% | 8 | 0 | MEDIUM
Compliance | 2 | 12 | 3 | 75% | 12 | 0 | HIGH
Operational | 2 | 10.5 | 3 | 71.43% | 12 | 0 | MEDIUM
Key Findings & Recommendations
🔴 CRITICAL | Ransomware & SQL Injection pose the highest inherent risk (Score: 20). Immediate EDR deployment and WAF implementation required.
🔴 CRITICAL | Zero-day exploits and supply-chain attacks carry catastrophic impact (Score: 10). Virtual patching and SBOM program must be initiated within 30 days.
🟡 HIGH | Phishing (TR-01), Cloud misconfiguration (TR-08), and API key leakage (TR-09) have high likelihood. MFA, CSPM, and secrets scanning are quick wins.
🟡 HIGH | Accidental DB deletion (TR-15) carries 5 impact with no backup controls. Automated backup + change management must be prioritized.
🟢 POSITIVE | After implementing all documented mitigations, estimated portfolio residual risk reduces by approximately 42%, from avg score ~14.8 to ~8.6.
🟢 POSITIVE | Environmental risks (TR-18–TR-20) are manageable with moderate investment. Cloud migration of critical workloads will further reduce office-dependency risk.